June 14, 2023

(Via E-Mail)

Mr. Bally Saputra Datuk Janosati

President Director

Riyadh Group Indonesia

Head Quarter Office. Graha Menara Hijau, Suite 502. Jakarta, Indonesia

RE:

Financing Arrangement, Project Management, Conceptual Design Services 
Riyadh Group CyberJaya Healthcare Complex in Malaysia

MI P-1017-R

Dear Mr. Bally Datuk Janosati,

We are pleased to submit this fee proposal to you for financing arrangement, Planning, Conceptual 
design, procurement preparations, and project management services regarding the Riyadh Group 
CyberJaya Healthcare Complex in Malaysia.

I.    BACKGROUND

1.

The Riyadh Group in Indonesia (“RGI”) is developing a healthcare complex in CyberJaya Malaysia 
to American and International standards. The complex includes a hospital, a medical office 
building (“MOB”), and a medical college. The MOB includes an outpatient rehabilitation center. 
The hospital, MOB, and the medical college will be constructed on lots 30 and 31 of the 
development. The total land area of lots 30 and 31 is approximately 12 acres.

2.

RGI is seeking a long-term financing loan from the Export-Import Bank of the United States 
(EXIM). RGI will engage U.S.A. firms to export U.S.A. goods and services for the design, 
construction, and training. RGI will provide EXIM with a loan guarantee from a local bank 
acceptable to EXIM. There will be two EXIM loans: (a) an Engineering Multiplier Program Loan 
(“EMP Loan”) which will be used for the front-end engineering, planning, and feasibility work, 
and (b) the Construction Long-Term Loan (the “Long-Term Loan”). The Long-Term Loan value 
will be determined during the front-end engineering, planning, and feasibility work.

3.

McMullan International Inc. (“MI”) shall perform financing arrangement, planning, conceptual 
design, and program management services as specified in this agreement in accordance with the 
terms and conditions herein. To perform its services, McMullan International will engage the 
following U.S.A. firms:

•

HKS Architects

•

Interface Engineering

•

Global Health Services Network

•

Allegheny International

•

CC Solutions LLC

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

II.   SCOPE OF SERVICES

1.

Services prior to obtaining the EMP Loan (estimated at three months duration).

a)

Program Management Services:

•

Develop the requirements for the integrated work to be performed during the EMP 
Loan duration.

•

Establish the requirements for the planning, master planning, and conceptual design 
consultants’ contracts.

•

Coordinate with local consultants that are selected by RGI. The local consultants are to 
be directly engaged by RGI.

•

Assist RGI in establishing the requirements for the project feasibility study. RGI will 
select and directly engage the firm providing the feasibility study report.

•

Ensure that the consultants’ contracts (including local consultants and the feasibility 
study) are integrated and adhere to project requirements.

•

Review all contracts with RGI to ensure agreement regarding the scope and fees for 
work to be completed during the EMP Loan duration.

•

Coordinate with EXIM regarding requirements for this project.

•

Establish the requirements for developing the U.S.A. products and equipment list 
including estimated costs.

•

Develop a disbursement and payment schedule during the EMP Loan phase.

b)

Financing Arrangement Services:

•

Review project documentation.

•

Develop the application for the EMP Loan.

•

Develop other documents required by EXIM for the EMP Loan, including but not limited 
to the acquisition list, exporter’s certificate, and project presentations.

•

Credit evaluation and review of RGI documentation, including RGI’s bank that will 
guarantee the EMP Loan.

•

Lead negotiation on behalf of RGI with EXIM.

•

Coordination with EXIM staff and consultants as well as with other parties, such as the 
bank guarantor.

•

During the disbursement period for the EMP Loan, obtain required documents from the 
borrower and the suppliers and prepare disbursement packages for EXIM.

2.

Services During the EMP Loan Phase (estimated at eight months duration).

a)

Planning Services: The planning work will be performed by U.S.A. firms with support from 
local firms. These services will start at the initiation of the EMP Loan phase and will be 
completed by the end of the third month from the initiation of the EMP Loan phase.

2

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

•

Perform an assessment of the hospital and the MOB proposed functions and 
specialties. Provide patient volume projection for each specialty.

•

Perform visits to Indonesia and Malaysia. Meet with hospitals and clinics that will direct 
Indonesian patients to the hospital and MOB in Malaysia.

•

Provide medical planning that includes functional and space programs for the hospital 
and the MOB.

•

Provide the hospital and the MOB organizational structure.

•

Provide the hospital and MOB anticipated operational expenses including staff salaries.

•

Provide medical equipment planning and develop the equipment list.

•

Provide education planning for the medical college including functional and space 
programs.

•

Provide the medical college organizational structure.

•

Provide the medical college anticipated operational expenses including staff salaries.

b)

Master Planning Services: The master planning work will be performed by U.S.A. firms 
assisted by local consultants. These services will start at the beginning of the second month 
from the initiation of the EMP Loan phase and will be completed by the end of the fourth 
month from the initiation of the EMP Loan phase.

•

Perform site visit.

•

Meet with RGI’s local consultants and obtain information regarding local jurisdiction 
requirements and site-specific requirements including but not limited to maximum built 
up area, height limitation, and easements.

•

Evaluate with the local consultants the need to develop a traffic study and analysis 
report.

•

Perform a site evaluation and assessment based on information provided by the local 
consultants. The information provided by the local consultants should include:

✓ Site survey including availability of site utilities (site utilities connections’ location

and capacity).

✓ Any available geotechnical information. 
✓ Environmental site assessment.

•

Upon completion of the site evaluation and assessment, provide three initial master 
planning options.

•

Present the three initial options to RGI for review and approval. RGI will select an option 
to be further developed.

•

Develop and finalize the master planning option that was selected by RGI.

c)

Conceptual Design Services: The conceptual design work will be performed by U.S.A. firms 
assisted by local consultants. These services will start at the beginning of the fifth month 
from initiation of the EMP Loan phase and will be completed by the end of seventh month 
from the initiation of the EMP Loan phase.

•

Upon completion of the final master plan and obtaining the necessary information from 
the feasibility study, develop a conceptual design for each facility.

3

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

•

The conceptual design phase scope of work will be as defined by AIA. Typically, 
conceptual design represents approximately five percent (5%) of final design 
documents.

•

Coordinate with RGI and the local consultants during the conceptual design work.

•

The conceptual design will include the following services: 
✓ Architectural

✓ Mechanical, Electrical, Plumbing

✓ Cost Modeling

d)

Program Management Services: work will be performed by U.S.A. firms. This work will 
start from the initiation of the EMP Loan phase and will be completed at the end of the 
eighth month from the initiation of the EMP Loan phase:

•

Develop and maintain the Project Responsibility Matrix for all members of the project 
team. This document will be the basis for establishing the roles, responsibilities, and 
overall communication structure.

•

Facilitate Target Value Design meetings to ensure the project adheres to the established 
budget. Conduct team pull scheduling sessions to establish baseline tasks and timelines 
to achieve the Project Schedule objectives.

•

Develop and maintain the Project Master Schedule.

•

Coordinate with the project team and RGI on all key decisions and assumptions 
impacting the quality, efficiency, and cost of the project to confirm it remains within 
budgetary constraints. Coordinate and maintain the communications log.

•

Coordinate with local consultants. Ensure that local consultant work is coordinated with 
U.S.A. consultant work.

e)

U.S.A. Product Procurement List Preparation Services: work will be performed by U.S.A. 
firms. These services will start from the beginning of the sixth month from the initiation of 
the EMP Loan phase and will be completed at the end of the eighth month from the 
initiation of the EMP Loan phase.

•

Provide initial U.S.A. product list including architectural, exterior envelope, MEP, 
medical equipment, medical furniture, prefabricated and modular systems, laboratory 
equipment, consumables, and others. Also provide initial U.S.A. services list.

•

Establish a single document that includes all initial equipment with corresponding cost.

•

Coordinate with EXIM requirements such as developing a small business vendor list 
from which some products will be provided and determine the percentage 
manufactured in the U.S.A.

•

Coordinate with manufacturers as to cost escalation and procurement and production 
timeline.

•

Determine the payment requirements and payment schedule for each manufacturer.

•

Provide recommendation report including scheduling and costing.

4

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

a.

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

f)

Financing Arrangement Services: services to obtain the Long-Term Loan will start 
beginning of second month from the initiation of the EMP Loan phase and will be 
completed at the end of eight month from the initiation of the EMP Loan phase.

•

Develop a financial application for the Long-Term Loan.

•

Develop other documents required by EXIM for the Long-Term Loan, including but not 
limited to the acquisition list, exporter’s certificate, project presentations.

•

Credit and feasibility evaluation. Lead negotiation on behalf of RGI with EXIM.

•

Develop the Long-Term Loan disbursement and payment schedule.

•

Coordination with EXIM staff and consultants as well as with other parties, such as the 
bank guarantor.

3.

Services During Final Design and Construction Phase: These services are not included in in this

agreement, however they could include:

a)

Program Management Services: Scope of work and fee will be determined during the EMP 
Loan phase.

b)

Schematic and Bridging Design Services: Scope of work and fee will be determined during 
the EMP Loan phase.

c)

U.S.A. Products Procurement Services Indicated in Item 2.b: Scope of work and fee will be 
determined during the EMP Loan phase.

d)

Hospital and Medical College Pre-Operations Services: Scope of work and fee will be 
determined during the EMP Loan phase.

III.  FEES AND PAYMENT

1.

Fees for Services Prior to Obtaining the EMP Loan are divided into monthly fees and success 
fees.

The monthly fees total:

$48,000

•

Initial payment is due prior to start of work:

$16,000.

•

Second payment is due 30 days from start of work:

$16,000.

•

Third payment is due 60 days from start of work:

$16,000.

5

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

2.

Financing Arrangement Services: The fee for the financing arrangement of the Long-Term 
Loan  is based on a success fee equal to 0.8% of the total amount of the Long-Term Loan. 
This fee shall be paid in three equal installments:

•

The first payment is due within 30 days of obtaining the EXIM approval to finance the 
Long-Term Loan.

•

The second payment is due within 120 days of obtaining the EXIM approval to finance 
the Long-Term Loan.

•

The third payment is due within 210 days of obtaining the EXIM approval to finance the 
Long-Term Loan.

3.

Commencement of Work

Work will commence upon receipt of a signed copy of this proposal and receipt of initial 
payments for each phase.

4.

Currency of Payment

All payments shall be paid to McMullan International in U.S. Dollars.

IV.   GENERAL CONDITIONS

1.

Limited of Term

This proposal must be accepted within three months, or the fees must be renegotiated.

2.

Additional Services

It is understood that RGI might ask for additional program and project management services. 
Fees for the additional services will be negotiated between the parties depending on the scope 
of work.

6

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

3.

Termination

The obligation to provide further services under this Agreement may be terminated by either 
party upon 30 days written notice in the event of substantial failure by the other party to 
perform in accordance with the terms herein through no fault of the terminating party. In the 
event of termination, MI will be paid for all services rendered to the date of termination. This 
termination clause only applies to program and project management service and does not apply 
to the arrangement of financing.

4.

Indemnification

RGI shall indemnify, defend and hold harmless MI, and all of its personnel, from and against any 
and all claims, damages, losses and expenses (including reasonable attorney's fees) arising out 
of or resulting from the performance of the services, provided that any such claims, damage, 
loss or expense are caused in whole or in part by the negligent act or omission and/or strict 
liability of RGI, anyone employed or retained by RGI, and anyone else for whom RGI may be 
legally liable.

5.

Third Party Beneficiary

The RGI and MI agree that the services to be performed by MI pursuant to this Agreement are 
solely for the benefit of RGI and are not intended by either MI or RGI to benefit any other 
person or entity. To the extent that any other person or entity benefits by the services 
performed by MI pursuant to this Agreement, such benefit is purely incidental and such other 
party shall not be deemed a third-party beneficiary to this Agreement.

6.

Personal Liability

In the event of any dispute or claim between RGI and MI arising out of or in connection with the 
project, RGI and MI agree that they shall look solely to each other for the satisfaction of any 
such dispute or claim. Moreover, notwithstanding anything to the contrary contained in any 
other provision of this Agreement, MI’s, and RGI’s shareholders, principals, partners, members, 
agents, directors, officers and/or employees shall have no personal liability whatsoever arising 
out of or in connection with this Agreement or the performance of services hereunder.

7.

Suspension of the Project

If the project is suspended for more than thirty (30) calendar days in the aggregate, MI shall be 
compensated for services performed and charges incurred prior to receipt of notice to suspend 
and, upon resumption, an equitable adjustment in fees to accommodate the resulting 
demobilization and remobilization costs. If the project is suspended for more than ninety (90) 
calendar days in the aggregate, MI may, at their option, terminate this Agreement upon giving 
notice in writing to the RGI.

7

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

8.

Successors

The RGI and MI, each bind itself as well as its successors and assigns to the other party of this 
Agreement and to the successors and assigns of such other party in respect to all covenants and 
obligations of this Agreement.

9.

Assignment

Neither RGI nor MI shall assign this Agreement, any rights thereunder or any causes of action 
arising therefrom without the written consent of the other. Any purported assignment or 
transfer, except as noted above, shall be deemed null, void, and invalid, the assignee shall 
acquire no rights as a result of such purported assignment or transfer and the non-assigning 
party shall not recognize any such purported assignment or transfer.

10.

Disputes Resolution

11.

All claims, counterclaims, disputes, and other matters in question between the parties hereto 
arising out of the relating to this Agreement or breach thereof will be presented to non-binding 
mediation with a mediator from the McCammon Group, as a precondition to filing of litigation in 
the Circuit Court of Fairfax County, Virginia.

Governing Law

This Agreement has been executed and delivered, and will be interpreted, construed, and 
enforced pursuant to and in accordance with the laws of England, for which all disputes arising 
from the interpretation, implementation, or termination of this Agreement shall have to be 
conclusively settled via arbitration at The London Court of International Arbitration (LCIA), in 
accordance with LCIA Arbitration Rules (“Arbitration Rules”), and through an arbitration board 
comprising three arbitrators who shall be nominated and summoned up in accordance with the 
Arbitration Rules then in effect. All proceedings shall be in the English language.

8

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651

Mr. Bally Saputra Datuk Janosati 
Riyadh Group Indonesia

June14, 2023

By signing this Agreement, the individual warrants that he/she has the legal authority to bind their 
company to this Agreement.

We trust the preceding meets with your approval. Please confirm your approval and acceptance of the 
forgoing terms and conditions by signing below and returning a copy for our records.

Offered by:

McMullan International, Inc.

Accepted by:

Pt. Riyadh Group Indonesia

Mohammed A. Ghosheh 
President

Bally Saputra Datuk Janosati 
President Director

Date

Date

9

McMullan International, Inc.        Project Management

11800 Sunrise Valley Drive, Suite 430         Reston, Virginia 20191

Telephone: (703) 556-0651